## Sheet1
S NO | MODULES | SUB-MODULES | MEMBERS INVOLVED | Start Time | End Time
1 | Home + Dashboard + Login / Register | Home Page (UI) | Rupika, Hayath | 13-08-2020 9.30 AM | 13-08-2020 01:00 PM
|  | Login Page | Jeethendra kumar, Roshan | 13-08-2020 02:00 PM | 13-08-2020 06:00 PM
|  | Registration | Jeethendra kumar, Roshan, Karthik | 13-08-2020 9.30 AM | 13-08-2020 01:00 PM
|  | Dashboard | Rupika, Hayath, Karthik | 13-08-2020 02:00 PM | 13-08-2020 06:00 PM
2 | Plans + New offers | Pre-Paid | Rupika Hayath Jeethendra | 14-08-2020 09:30 AM | 14-08-2020 03:00 PM
|  | Post-Paid | Karthik Roshan Hayath | 14-08-2020 09:30 AM | 14-08-2020 03:00 PM
|  | BroadBand | Rupika Jeethandera Roshan | 14-08-2020 03:00 PM | 14-08-2020 06:00 PM
3 | Billing | Billing Portal | Roshan Jeethendra Karthik | 15-08-2020 09:30 AM | 16-08-2020 11:00 AM
|  | Payment Gateway | Hayath Rupika | 15-08-2020 09:30 AM | 16-08-2020 11:00 AM
|  | SMS & Email Notification | Karthik | 2020-08-15 11:00 | 17:00
4 | Customer Support | FAQs | Jeethendra Rupika | 16-08-2020 11:00 AM | 16-08-2020 06:00 PM
|  | Complaint Register | Hayath Roshan Karthik | 16-08-2020 11:00 AM | 16-08-2020 06:00 PM
5 | Bill History | Bill History Page | Karthik Roshan | 17-08-2020 09:30 AM | 18-08-2020 10:00 PM
6 | Admin Panel | CRUD | All Members | 18-08-2020 11:00AM | 18-08-2020 01:00 PM
7 | Deployment & System Testing | Flow testing | All members | 18-08-2020 02:00 PM | 18-08-2020 06:00 PM